FORGE CYBER DEFENSE

Service-Disabled Veteran-Owned Small Business (SDVOSB)

Control Data Seeding &

Forge Reporter Readiness

Implementation Plan

Version 1.0  |  March 2026

CONFIDENTIAL — FOR INTERNAL USE ONLY

# 1. Situation Assessment

This section presents the current state of the ForgeComply 360 production database as of March 5, 2026, identifies the gap between what exists and what Forge Reporter (and paying customers) require, and establishes the scope of work.

## 1.1 Current Production State

| Metric | Current Value | Required for FedRAMP Mod | Gap |
| --- | --- | --- | --- |
| NIST 800-53 Control Definitions | 585 (20 families) | 1,189 (full Rev 5 catalog) | 604 definitions missing |
| FedRAMP Moderate Baseline Tags | 265 tagged baseline_moderate=1 | 325 controls | 60 baseline tags missing |
| Control Implementations | 35 total (2 systems) | 325 per system minimum | 290+ per system |
| Systems with Implementations | 2 of 8 (MFEHR=30, SCPP=5) | All active systems | 6 systems at zero |
| POA&Ms | 14 | Realistic per-system set | Need severity-distributed set |
| Assets | 31 | 50–100 per moderate system | Under-seeded |
| Vulnerability Findings | 28 | 100–300 per scan cycle | Under-seeded |
| SSP Documents | 2 | 1 per system in ATO | Adequate for now |
| Other Frameworks (FedRAMP, CMMC, etc.) | 0 definitions each | Framework-specific controls | 9 empty frameworks |

Key Finding: The 585 NIST 800-53 definitions cover all 20 families but are missing roughly half the catalog (enhancements and PM-family controls). More critically, only 35 control implementations exist across 2 systems, covering less than 11% of FedRAMP Moderate for a single system. Forge Reporter Section 15 (Control Implementations) will show a near-empty table for any system except MFEHR.

## 1.2 Forge Reporter Dependencies

The Forge Reporter (https://reporter-forgecomply360.pages.dev) is a 23-section FISMA/FedRAMP SSP authoring wizard. In Connected Mode, it pulls data from the ForgeComply 360 API. The following backend data directly feeds Reporter sections:

| Reporter Section | Backend Data Required | Current Coverage |
| --- | --- | --- |
| S1: System Information | systems table (name, acronym, impact_level, boundary) | 8 systems seeded — OK |
| S2: FIPS 199 Categorization | systems (confidentiality/integrity/availability_impact) | All 8 have levels — OK |
| S4: Control Baseline | control_definitions with baseline_low/moderate/high flags | 265 of 325 moderate — PARTIAL |
| S9: Ports, Protocols & Services | assets (open_ports, ip_address, hostname) | 31 assets, no open_ports — GAP |
| S12: Personnel & Roles | users (role, first_name, last_name) | Users exist — OK |
| S15: Control Implementations | control_implementations (narrative, status, responsibility) | 35 of 325 needed — CRITICAL GAP |
| S23: POA&M | poams (weakness, milestones, risk_level, status) | 14 POA&Ms — PARTIAL |

Bottom Line: Section 15 (Control Implementations) is the single biggest blocker. A FedRAMP Moderate SSP requires narrative for all 325 baseline controls. The current 35 implementations cover roughly 10% of one system. Until this is populated, Forge Reporter in Connected Mode cannot produce a credible demo SSP.

# 2. Implementation Strategy

The work divides into three phases executed over 3 weeks. Phase 1 (control definitions) unblocks everything else. Phase 2 (implementations + narratives) is the heavy lift. Phase 3 (supporting data) rounds out the demo experience.

## 2.1 Phase 1: Complete NIST 800-53 Rev 5 Catalog (Week 1)

### 2.1.1 Objective

Bring control_definitions from 585 to the full 1,189 NIST 800-53 Rev 5 catalog, correctly tag all baseline flags, and populate the 9 empty framework records.

### 2.1.2 Data Source

The authoritative source is the NIST SP 800-53 Rev 5 control catalog published in OSCAL JSON format at https://github.com/usnistgov/oscal-content. The OSCAL catalog JSON contains every control, enhancement, family, description, guidance, related controls, and baseline allocation. We parse this directly rather than manually entering data.

### 2.1.3 Tasks

| Task ID | Description | Method | Effort |
| --- | --- | --- | --- |
| P1-T1 | Download NIST OSCAL catalog JSON (800-53 Rev 5) | Script fetches from NIST GitHub | 1 hr |
| P1-T2 | Parse catalog: extract all controls + enhancements | Node.js parser maps OSCAL to DB schema | 4 hrs |
| P1-T3 | Deduplicate against existing 585 rows; INSERT remaining 604 | SQL INSERT OR IGNORE on (framework_id, control_id) | 2 hrs |
| P1-T4 | Validate baseline flags: cross-reference OSCAL baselines JSON | Script checks baseline_low/moderate/high against SP 800-53B | 2 hrs |
| P1-T5 | Populate FedRAMP framework definitions by cloning NIST + overlay | FedRAMP baselines from OSCAL resolved profiles | 4 hrs |
| P1-T6 | Populate CMMC Level 2 (110 practices mapped to 800-171) | CMMC mapping table from DoD | 3 hrs |
| P1-T7 | Populate NIST 800-171 Rev 3 (110 CUI controls) | OSCAL 800-171 catalog | 2 hrs |
| P1-T8 | Populate HIPAA, SOC 2, StateRAMP cross-mappings | Manual mapping tables + NIST crosswalks | 4 hrs |
| P1-T9 | Validation: COUNT by family matches NIST publication | Automated test script | 1 hr |

Exit Criteria: control_definitions table has 1,189 rows for NIST 800-53, all baseline flags validated, FedRAMP/CMMC/800-171 frameworks populated. SELECT COUNT(*) matches published control counts per framework.

## 2.2 Phase 2: Seed Control Implementations (Week 2)

### 2.2.1 Objective

Generate realistic control implementation records for at least 2 demo systems covering the full FedRAMP Moderate baseline (325 controls each), with professional-quality narratives suitable for SSP authoring and 3PAO review.

### 2.2.2 Narrative Generation Strategy

Each control implementation requires a narrative describing HOW the organization implements the control. These narratives must be system-specific, reference concrete technologies, and follow the FedRAMP narrative pattern: (1) state what is done, (2) identify the responsible party, (3) reference the policy/procedure, (4) describe the technical mechanism, (5) state the frequency/trigger.

We will use a tiered approach to generate 650+ narratives (325 per system for 2 systems):

| Tier | Controls | Count | Narrative Method |
| --- | --- | --- | --- |
| Tier 1: Technical Controls | AC-2 through AC-7, AU-*, CM-*, IA-*, SC-*, SI-* | ~180/system | AI-generated from system context + technology stack; each 150–300 words |
| Tier 2: Operational Controls | AT-*, CP-*, IR-*, MA-*, MP-*, PE-*, PS-* | ~90/system | Template-based with system-specific substitution; each 100–200 words |
| Tier 3: Management Controls | CA-*, PL-*, PM-*, RA-*, SA-*, SR-* | ~55/system | Policy-reference narratives with org-specific details; each 80–150 words |

### 2.2.3 System Profiles for Narrative Context

| Attribute | MFEHR (Healthcare EHR) | FC360 (ForgeComply Platform) |
| --- | --- | --- |
| Impact Level | FIPS 199 Moderate | FIPS 199 Moderate |
| Hosting | AWS GovCloud (IL2) | Cloudflare Workers + D1 |
| Auth Stack | Okta SSO + MFA, Azure AD federation | JWT + PBKDF2, TOTP MFA |
| Database | PostgreSQL RDS (encrypted) | Cloudflare D1 (AES-256) |
| Monitoring | Splunk SIEM, CrowdStrike EDR | Cloudflare Analytics, custom SOC |
| Key Policy Doc | PHS-POL-xxx series | FCD-POL-xxx series |
| Responsible Org | Patriot Health Systems | Forge Cyber Defense |

### 2.2.4 Tasks

| Task ID | Description | Method | Effort |
| --- | --- | --- | --- |
| P2-T1 | Build narrative generation script with system profiles | Node.js + Claude API for Tier 1 | 8 hrs |
| P2-T2 | Generate 325 implementations for MFEHR system | Script execution + QA review | 6 hrs |
| P2-T3 | Generate 325 implementations for FC360 system | Script with ForgeComply context | 6 hrs |
| P2-T4 | Set implementation_status distribution (see below) | SQL UPDATE based on control family | 2 hrs |
| P2-T5 | Set responsibility distribution (provider/customer/shared) | SQL UPDATE per hosting model | 2 hrs |
| P2-T6 | QA: spot-check 50 narratives against FedRAMP SSP Appendix A template | Manual review | 4 hrs |
| P2-T7 | Verify Forge Reporter Section 15 renders all 325 controls | End-to-end test in Connected Mode | 2 hrs |

### 2.2.5 Target Status Distribution

A realistic system at Day 45 of a 90-day ATO timeline should show progress, not perfection:

| Implementation Status | Target % | Count (of 325) | Rationale |
| --- | --- | --- | --- |
| Implemented | 60% | ~195 | Core technical + operational controls in place |
| Partially Implemented | 20% | ~65 | In-progress items, typically complex controls |
| Planned | 12% | ~39 | Controls awaiting infrastructure or policy finalization |
| Alternative | 3% | ~10 | Compensating controls documented |
| Not Applicable | 5% | ~16 | Controls scoped out (e.g., PE for cloud-only systems) |

## 2.3 Phase 3: Supporting Data Enrichment (Week 3)

### 2.3.1 Objective

Populate assets, vulnerability findings, POA&Ms, and evidence linkages so that Reporter sections 9, 23, and the overall dashboard present realistic operational data.

### 2.3.2 Tasks

| Task ID | Description | Method | Effort |
| --- | --- | --- | --- |
| P3-T1 | Seed 75 assets for MFEHR (servers, endpoints, network, cloud) | SQL INSERT with realistic IPs, FQDNs, OS versions | 3 hrs |
| P3-T2 | Add open_ports JSON to assets for S9 (Ports/Protocols) | UPDATE assets SET open_ports where relevant | 1 hr |
| P3-T3 | Generate 150 vulnerability findings (10% crit, 25% high, 35% med, 30% low) | Seed from real CVE data + Nessus plugin patterns | 4 hrs |
| P3-T4 | Generate 40 POA&Ms from critical+high findings with milestones | Script using POA&M generation logic from Nessus design | 3 hrs |
| P3-T5 | Link POA&Ms to control_implementations via control_implementation_id | SQL UPDATE after generation | 1 hr |
| P3-T6 | Seed vulnerability_definitions table (CVE catalog entries) | Bulk INSERT from NVD-style data | 2 hrs |
| P3-T7 | Create scan_imports table (if not exists) for Nessus integration | D1 migration SQL from design doc | 1 hr |
| P3-T8 | End-to-end Forge Reporter validation in Connected Mode | Walk all 23 sections, verify data renders | 4 hrs |

# 3. Execution Timeline

| Week | Phase | Key Deliverables | Hours | Dependencies |
| --- | --- | --- | --- | --- |
| Week 1 | Phase 1: Control Catalog | 1,189 NIST controls, FedRAMP/CMMC/171 frameworks populated | 23 hrs | NIST OSCAL JSON access |
| Week 2 | Phase 2: Implementations | 650+ implementations with narratives for 2 systems | 30 hrs | Phase 1 complete |
| Week 3 | Phase 3: Supporting Data | Assets, vulns, POA&Ms, Nessus schema, Reporter validation | 19 hrs | Phase 2 complete |

Total Estimated Effort: 72 hours across 3 weeks. This can be compressed to 2 weeks with parallel execution of Phase 1 and early Phase 2 tasks.

# 4. Technical Approach

## 4.1 Control Catalog Seeding Script

The seeding script will be a Node.js module that executes D1 queries through the Cloudflare API (or Wrangler CLI). Key design decisions:

| Decision | Choice | Rationale |
| --- | --- | --- |
| Data Source | NIST OSCAL JSON catalog from usnistgov/oscal-content | Authoritative, machine-readable, includes enhancements |
| Execution Target | D1 database via Cloudflare Workers or direct D1 HTTP API | Avoids Wrangler CLI dependency; Stan prefers web UI methods |
| Batch Size | 50 INSERTs per batch (D1 transaction limit) | D1 has 1000-statement transaction limit; safe batching |
| Deduplication | INSERT OR IGNORE on UNIQUE(framework_id, control_id) | Preserves existing 585 rows, adds only missing |
| Baseline Mapping | Cross-reference SP 800-53B baselines OSCAL profile | Ensures baseline_low/moderate/high flags are accurate |

## 4.2 Narrative Generation Architecture

Control narratives are generated using a two-pass approach:

Pass 1 (Template Fill): For each of the 325 FedRAMP Moderate controls, a narrative template is populated with system-specific context (hosting environment, authentication stack, monitoring tools, responsible organization). Templates follow the standard FedRAMP narrative pattern and reference specific policy document numbers.

Pass 2 (AI Enhancement): Tier 1 technical controls are enhanced using the Claude API to add implementation-specific detail, technology references, and configuration parameters. The AI prompt includes the control description, system profile, and the template narrative as a starting point.

All generated narratives are stored in the control_implementations.implementation_narrative column and are immediately available to Forge Reporter Section 15 via the existing API endpoint GET /api/v1/controls/{id}/implementation.

## 4.3 Database Migration for Nessus Integration

Phase 3 includes executing the scan_imports table creation SQL from the Nessus Integration Design Document (v1.0, Feb 2026). This migration also adds the required columns to vulnerability_findings and assets tables, enabling the full import workflow once development begins.

# 5. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| D1 batch insert rate limiting causes timeout on 604-row INSERT | Medium | Medium | Batch in groups of 50; add retry logic with exponential backoff |
| AI-generated narratives contain generic/hallucinated content | Medium | High | QA checkpoint at P2-T6; spot-check against FedRAMP Appendix A format |
| OSCAL baseline JSON format changes between NIST releases | Low | High | Pin to specific OSCAL catalog release (v5.1.1); validate checksums |
| Forge Reporter Connected Mode API contract differs from seeded data | Medium | High | Test Reporter against staging before production push; review sspMapper.ts |
| Existing 585 control definitions have incorrect family/baseline data | Low | Medium | Phase 1 includes validation step (P1-T9) comparing against NIST publication |

# 6. Success Metrics

| Metric | Current | Target | Measurement |
| --- | --- | --- | --- |
| NIST 800-53 control definitions | 585 | 1,189 | SELECT COUNT(*) FROM control_definitions WHERE framework = NIST |
| FedRAMP Moderate baseline coverage | 265/325 tagged | 325/325 | SELECT COUNT(*) WHERE baseline_moderate = 1 |
| Control implementations per system | 35 (2 systems) | 325 per system (2 systems) | SELECT COUNT(*) FROM control_implementations WHERE system_id = X |
| Implementation narrative completeness | ~30 have narratives | 650+ narratives | SELECT COUNT(*) WHERE implementation_narrative IS NOT NULL |
| Forge Reporter S15 render test | Untested | All 325 controls visible | Manual walkthrough in Connected Mode |
| Non-NIST frameworks populated | 0 of 9 | At least 4 (FedRAMP, CMMC, 171, HIPAA) | SELECT COUNT(*) per framework_id |
| Assets per demo system | 31 total | 75+ for MFEHR | SELECT COUNT(*) FROM assets WHERE system_id = MFEHR |
| Vulnerability findings | 28 | 150+ | SELECT COUNT(*) FROM vulnerability_findings |
| POA&Ms with milestones | 14 | 40+ with structured milestones JSON | SELECT COUNT(*) WHERE milestones != '[]' |

# 7. Appendix A: Current Database Schema Summary

Production D1 database ID: fe250bed-40a9-443a-a6c7-4b59bf8a0dac. Schema as of March 5, 2026.

## 7.1 Core Tables Relevant to This Plan

| Table | Row Count | Key Columns | Notes |
| --- | --- | --- | --- |
| organizations | 1+ | id, name, slug, subscription_tier | Multi-tenant root entity |
| systems | 8 | id, org_id, name, acronym, impact_level | MFEHR and SCPP have implementations |
| compliance_frameworks | 10 | id, short_name, version | Only NIST 800-53 has definitions |
| control_definitions | 585 | id, framework_id, control_id, family, baseline_* | 20 families; 265 tagged moderate |
| control_implementations | 35 | id, system_id, control_def_id, narrative, status | 30 for MFEHR, 5 for SCPP |
| poams | 14 | id, org_id, system_id, weakness_name, risk_level | Need milestones enrichment |
| assets | 31 | id, org_id, system_id, hostname, ip_address | Missing open_ports, fqdn |
| vulnerability_findings | 28 | id, org_id, asset_id, severity, status | Missing Nessus-specific columns |
| ssp_documents | 2 | id, system_id, version, status, oscal_json | Adequate for current phase |
| security_controls | 145 | id, control_id, family, title | Legacy table; consider deprecating |

## 7.2 Duplicate Table Issue: security_controls vs. control_definitions

The database contains both a security_controls table (145 rows, no framework_id FK) and a control_definitions table (585 rows, properly linked to compliance_frameworks). The control_definitions table is the correct entity used by control_implementations and should be the sole source of truth. The security_controls table appears to be from an earlier schema iteration and should be deprecated or migrated to avoid confusion during seeding.

# 8. Appendix B: Forge Reporter Architecture Notes

Forge Reporter is a React 19 + TypeScript + Vite application deployed to Cloudflare Pages. Key architectural points relevant to the seeding plan:

### Connected Mode Data Flow

Reporter authenticates via URL hash parameters (#token=JWT&ssp=ID&api=URL) and syncs bidirectionally with the ForgeComply 360 API. The sspMapper service (871 lines) transforms between the Reporter's internal SSPData type (294 fields) and the backend API format. Control implementations populate Section 15 via the controls API endpoint.

### Offline Mode Fallback

In Offline Mode, Reporter uses localStorage. This means the seeding work primarily impacts Connected Mode demos. However, a fully seeded backend also enables pre-populating the offline cache for air-gapped demo scenarios by exporting OSCAL JSON from the API and importing into Reporter.

### OSCAL Validation

Reporter validates exports against the NIST OSCAL 1.1.2 SSP JSON Schema using Ajv. The seeded control data must produce valid OSCAL output. This means control_id values must match NIST naming conventions (e.g., 'ac-1' lowercase in OSCAL, though stored as 'AC-1' in D1), and implementation narratives must be non-empty strings for implemented controls.

# 9. Immediate Next Actions

| Priority | Action | Owner | Due |
| --- | --- | --- | --- |
| P0 | Approve this plan and confirm 2-system scope (MFEHR + FC360) | Stan | Day 1 |
| P0 | Begin Phase 1 execution: download NIST OSCAL catalog | Engineering | Day 1 |
| P1 | Resolve security_controls vs. control_definitions duplication | Engineering | Day 2 |
| P1 | Set up Claude API narrative generation pipeline | Engineering | Day 3 |
| P2 | Identify 50 spot-check controls for QA review (P2-T6) | Stan | Day 7 |
| P2 | Coordinate with sample dataset package work (DVHT/PHP Nessus files) | Engineering | Day 10 |

This plan is designed to be executed iteratively. Phase 1 can begin immediately. Each phase produces independently valuable output: Phase 1 gives a complete control catalog for all framework browsing, Phase 2 unlocks Forge Reporter demos, and Phase 3 enables the full vulnerability management and POA&M workflow demonstration.

— END OF DOCUMENT —